{"text_format":"2","workbook":"xls","n_sheets":1,"sheets":["Sheet0"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":0,"defined_names":0,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900","formulas":"cached_only"}

{"sheet":"Sheet0","index":0,"n_rows":33,"n_cols":12,"rows_kept":33,"cut":false,"hidden":false,"merged":[[0,0,0,11],[1,0,1,1],[1,2,1,11],[2,0,2,1],[2,2,2,5],[2,6,2,7],[2,8,2,11],[3,4,3,5],[3,6,3,7],[3,9,3,10],[4,4,4,5],[4,6,4,7],[4,9,4,10],[5,4,5,5],[5,6,5,7],[5,9,5,10],[6,4,6,5],[6,6,6,7],[6,9,6,10],[7,4,7,5],[7,6,7,7],[7,9,7,10],[8,2,8,6],[8,7,8,11],[9,2,9,6],[9,7,9,11],[22,0,22,8],[31,7,31,8],[31,9,31,11],[32,7,32,11],[11,0,21,0],[11,1,18,1],[19,1,20,1],[11,2,12,2],[13,2,14,2],[15,2,16,2],[17,2,18,2],[3,0,7,1],[8,0,9,1],[23,7,30,11]],"flags":["formulas_cached_only"]}
["项目支出绩效自评表\n(2024年度）"]
["项目名称",null,"现代职业教育质量提升计划专项资金"]
["主管部门",null,"包头市教育局（部门）",null,null,null,"实施单位",null,"包头职业教育园区综合服务中心"]
["项目资金\n（万元）",null,null,"年初预算数","全年预算数",null,"全年执行数",null,"分值","执行率（%）",null,"得分"]
[null,null,"年度资金总额","0","596",null,"421.06",null,"10","70.65",null,"7.06"]
[null,null,"其中：财政拨款","0","596",null,"421.06",null,"——","70.65",null,"——"]
[null,null,"上年结转资金","","",null,"",null,"——","",null,"——"]
[null,null,"其他资金","0","0",null,"0",null,"——","0",null,"——"]
["年度总体目标",null,"预期目标",{"$nulls":4},"实际完成情况"]
[null,null,"  通过在园区内环路关键节点、段落加设步行道等设施，有效解决园区内环路人车混行带来的交通安全隐患问题，进一步美化园区环境，提升园区品质，为园区师生提供良好的工作、学习、生活环境，增强师生的获得感、幸福感、安全感。",{"$nulls":4}," 通过改造园区水电管网及改造园区供暖设施，有效解决园区公共区域用水用电问题及温度不达标问题，进一步美化园区环境，提升园区品质，为园区师生提供良好的工作、学习、生活环境，增强师生的获得感、幸福感、安全感。"]
["绩效指标","一级指标","二级指标","三级指标","指标性质","指标方向","年度指标值","实际完成值","计量单位","分值","得分","偏差原因分析及改进措施"]
["绩效指标","产出指标","数量指标","更换计量表具","正向","大于等于","52","224.00","套","8",8,""]
["绩效指标","产出指标","数量指标","分户改造户数","正向","大于等于","7","14.00","户","7",7,""]
["绩效指标","产出指标","质量指标","分户改造合格率","正向","大于等于","90","95.00","%","7",7,""]
["绩效指标","产出指标","质量指标","水电改造合格率","正向","大于等于","90","95.00","%","8",8,""]
["绩效指标","产出指标","时效指标","分户改造及时率","正向","大于等于","90","95.00","%","5",5,""]
["绩效指标","产出指标","时效指标","水电改造及时率","正向","大于等于","90","94.98","%","5",5,""]
["绩效指标","产出指标","成本指标","分户改造成本","反向","小于等于","20","20.00","万","5",5,""]
["绩效指标","产出指标","成本指标","水电改造成本","反向","小于等于","370","370.00","万","5",5,""]
["绩效指标","效益指标","社会效益指标","提升园区办学条件","定性","","效果显著","效果显著","","15",15,""]
["绩效指标","效益指标","可持续影响指标","促进职业教育园区健康发展","定性","","长期","长期","","15",15,""]
["绩效指标","满意度指标","服务对象满意度指标","园区师生满意度","正向","大于等于","90","95.00","%","10",10,""]
["总分",{"$nulls":8},"100","97.06"]
[{"$nulls":7},"(盖章)"]
{"$rows_empty":7}
[{"$nulls":7},"主管部门:",null,"包头市教育局（部门）"]
[{"$nulls":7},"年    月    日                     "]